## Sheet1
Risk ID | Asset / Process | Risk Description | Likelihood | Impact | Risk Score | Risk Rating | Mitigation | Owner | Status
R-01 | Employee accounts | MFA not enforced, increasing account takeover risk | 4 | 5 | 20 | Critical | IT Administrator | Open | Open
R-02 | Email | Phishing could expose employee credentials | 4 | 4 | 16 | High | Security Coordinator | Open | Open
R-03 | Laptops | Lost laptop could expose sensitive data if encryption is absent | 3 | 5 | 15 | High | IT Administrator | Open | Open
R-04 | User access | Former employee accounts may remain active | 3 | 4 | 12 | High | HR and IT | Open | Open
R-05 | Backups | Ransomware or deletion could make important files unrecoverable | 3 | 5 | 15 | High | IT Administrator | Open | Open
R-06 | Customer data | Excessive permissions could expose sensitive information | 3 | 4 | 12 | High | System Owners | Open | Open